## Defects
| Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks | Column 1 | Column 2 | Column 3
1 | Pattem Dolly Sai Iswarya | 2026-07-08 | Duplicate submission routes registered | Sprint1 | Pattem Dolly Sai Iswarya | User Interface | Removed duplicate APIs | 2026-07-09 | closed | verified successfully
2 | Pattem Dolly Sai Iswarya | 2026-07-10 | Frontend could not connect to backend | Sprint2 | Pattem Dolly Sai Iswarya | Logical | Updated backend endpoint | 2026-07-11 | closed | working
3 | Pattem Dolly Sai Iswarya | 2026-07-13 | Anthropic dependency removed | Sprint2 | Pattem Dolly Sai Iswarya | Maintainability | Migrated to Gemini API | 2026-07-15 | closed | API updated
4 | Pattem Dolly Sai Iswarya | 2026-07-16 | Flask dependency removed | Sprint2 | Pattem Dolly Sai Iswarya | User Interface | Installed Flask package | 2026-07-16 | Verified | resolved
5 | Pattem Dolly Sai Iswarya | 2026-07-18 | Gemini API key not loaded | Sprint2 | Pattem Dolly Sai Iswarya | Maintainability | Added .env loading | 2026-07-19 | closed | Verified
6 | Pattem Dolly Sai Iswarya | 2026-07-21 | RAG retrieval pipeline incomplete | Sprint2 | Pattem Dolly Sai Iswarya | Standards | Implementation ongoing | 2026-07-25 | Closed | Verified
7 | Pattem Dolly Sai Iswarya | 2026-07-24 | Remediation Agent response not mapped to findings | Sprint3 | Pattem Dolly Sai | Logical | Mapped remediation output with findings | 2026-07-26 | Closed | Verified
8 | Pattem Dolly Sai Iswarya | 2026-07-25 | PR Summary missing severity breakdown | Sprint3 | Pattem Dolly Sai | User Interface | Updated PR Summary generation | 2026-07-27 | Closed | Working
9 | Pattem Dolly Sai Iswarya | 2026-07-26 | Findings Dashboard not displaying remediation details | Sprint3 | Pattem Dolly Sai | User Interface | Updated dashboard UI | 2026-07-28 | Closed | Verified
10 | Pattem Dolly Sai Iswarya | 2026-07-27 | Overall Code Health Score not calculated | Sprint3 | Pattem Dolly Sai | Logical | Added health score computation | 2026-07-29 | Closed | Working
11 | Pattem Dolly Sai Iswarya | 2026-07-28 | AI Chat not retrieving knowledge base response | Sprint3 | Pattem Dolly Sai | Maintainability | Improved RAG retrieval integration | 2026-07-30 | Closed | Verified
12 | Pattem Dolly Sai Iswarya | 2026-07-29 | Dashboard summary cards not refreshing after analysis | Sprint3 | Pattem Dolly Sai | User Interface | Added automatic refresh logic | 2026-07-30 | Closed | Verified
13 | Pattem Dolly Sai Iswarya | 2026-08-01 | Report generation was incomplete | Sprint4 | Pattem Dolly Sai Iswarya | Logical | Implemented PDF, JSON and Markdown report generation | 2026-08-03 | Closed | verified
14 | Pattem Dolly Sai Iswarya | 2026-08-04 | Analysis history was not displaying previous submissions correctly | Sprint4 | Pattem Dolly Sai Iswarya | User Interface | Updated history retrieval and display logic | 2026-08-06 | Closed | verified
15 | Pattem Dolly Sai Iswarya | 2026-08-07 | Security findings were not consistently mapped to OWASP categories | Sprint4 | Pattem Dolly Sai Iswarya | Standards | Added CWE-to-OWASP mapping and updated security analysis | 2026-08-09 | Closed | verified
16 | Pattem Dolly Sai Iswarya | 2026-08-10 | End-to-end inspection workflow required final validation | Sprint4 | Pattem Dolly Sai Iswarya | Logical | Integrated submission, analysis, security, remediation and summary modules and performed validation | 2026-08-12 | Closed | verified
17 | Pattem Dolly Sai Iswarya | 13-08-1016 | Final system validation and milestone completion pending | Sprint4 | Pattem Dolly Sai Iswarya | User Interface | Completed integrated testing, fixed identified issues and finalized Milestone 4 deliverables | 2026-08-15 | Closed | verified
18

## Sheet2
Logical
User Interface
Maintainability
Standards
Others